## Feuille1
Activities	07.06				14.06				21.06				28.06				05.07				12.07				19.07				26.07				02.08				09.08				16.08				23.08				30.08				06.09				13.09				20.09				27.09				04.10				11.10				18.10				25.10				01.11				08.11				15.11				22.11				29.11				06.12				13.12				20.12				27.12
1. Collect a representative dataset of windband scores (Duration: 2 weeks)
Identify various sources for windband scores (1/2 week)
Gather the digital dataset from the identified sources (1/2 week)
Ensure the dataset covers a wide range of composers, styles, and difficulty levels (1/2 week)
Organize and curate the dataset for further processing (1/2 week)
2. Preprocess the collected dataset (Duration: 2 weeks)
Clean the images and remove any artifacts or noise (1/2 week)
Normalize the orientation and size of the pages (1/2 week)
Segment the individual parts of the score (1/2 week)
Validate the quality of the preprocessed dataset (1/2 week)
3. Define evaluation metrics (Duration: 2 weeks)
Research and identify appropriate performance indicators for OMR in windband scores (1.5 weeks)
Define and formulate evaluation metrics based on the identified indicators (1/2 week)
4. Implement a baseline OMR system (Duration: 2 weeks)
Study and understand existing open-source tools and techniques for OMR (1 weeks)
Select and adapt the most suitable tools for windband scores (1/2 week)
Implement the baseline system using the selected tools (1/2 week)
5. Explore machine learning techniques (Duration: 5 weeks)
Research and study convolutional neural networks (CNNs) for OMR (1 week)
Research and study recurrent neural networks (RNNs) for OMR (1 week)
Research and study deep belief networks (DBNs) for OMR (1 week)
Select the most promising techniques and develop models for windband scores (1 week)
Train and evaluate the models using the preprocessed dataset (1 week)
6. Investigate algorithmic and computational improvements (Duration: 1 month)
Research and explore advanced image processing methods for OMR (1 week)
Investigate more efficient data structures for OMR (1 week)
Study parallel computing techniques for OMR (1 week)
Implement and compare the performance of the identified improvements (1 week)
7. Develop a prototype OMR system (Duration: 1 months)
Incorporate the best techniques and methods from the previous steps (1 weeks)
Test and refine the prototype system based on feedback (3 weeks)
8. Test and validate the prototype system (Duration: 1 months)
Evaluate the system’s performance on both synthetic and real-world examples (1 week)
Compare the system’s results with manual transcription by human experts (1 week)
Analyze and validate the performance of the system (2 weeks)
9. Analyze results and discuss implications (Duration: 1 months)
Analyze the performance and accuracy of the OMR system (1 week)
Discuss the strengths, limitations, and implications of the proposed system (1week)
Discuss potential future research directions and applications for the system (2 weeks)